## MedVet Zoom Implementation
MedVet Zoom Implementation | [5 empty] | Powered by
Task ID | Name | Section/Column | Start Date | Due Date | Parent task | Status | Module | Duration | Assigned To | % Complete | Notes
1215137372993321 | SOW Executed | INITIATING |  | 2026-04-30 |  | Complete | Not Applicable | 1 day | PMO | 100%
1215150263848982 | Internal Kickoff Delivered | INITIATING | 2026-05-04 | 2026-05-08 |  | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100%
1215137372993479 | External Kickoff Delivered | INITIATING | 2026-05-04 | 2026-05-08 |  | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100%
1215137372993334 | Vendor Quotes Signed | INITIATING | 2026-05-04 | 2026-05-29 |  | Complete | Not Applicable | 1 day | Account Team | 100%
1215150263848981 | Project Set-Up | PLANNING | 2026-05-04 | 2026-05-08 |  | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100%
1215137372993459 | Add Stakeholders to SharePoint folder |  | 2026-05-04 | 2026-05-08 | Project Set-Up | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100%
1215137372993463 | Create Chat Channel |  | 2026-05-04 | 2026-05-08 | Project Set-Up | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100%
1215137372993466 | Schedule Project Meetings |  | 2026-05-04 | 2026-05-08 | Project Set-Up | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100% | Joining [CORE] UniComm Project Weekly Touchpoint Fridays 2:30pm EDT
1215137372993666 | Schedule Technical Meetings |  | 2026-05-04 | 2026-05-08 | Project Set-Up | Complete | Not Applicable | 5 days | Project Manager (Primary) | 100%
1215137372993477 | Confirm Admin Access |  | 2026-05-04 | 2026-05-08 | Project Set-Up | Complete | Not Applicable | 5 days | Engineer | 100%
1215137372993705 | Confirm Licenses and Hardware |  | 2026-05-04 | 2026-05-08 | Project Set-Up | Complete | Not Applicable | 5 days | Project Manager (Primary) | 25%
1215137372993341 | Technical Discovery | PLANNING | 2026-05-08 | 2026-07-02 |  | Complete | UCaaS | 15 days | Engineer, Customer | 100%
1215150228289635 | Schedule Design Workshop |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215150228289634 | Current-State Assessment Review |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215150228289628 | Data Gathering in Workbook Tab |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215137372993428 | Security, Firewall, and Access Requirements Provided |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100% | Benny provided port and firewall KB article.
1215137372993409 | Environment and Network Readiness |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215154152466711 | MedVet to confirm ports and firewalls are open |  |  |  | Environment and Network Readiness
1215154152466712 | MedVet to run network readiness tests |  |  |  | Environment and Network Readiness
1215137372993426 | SSO and Identity Configuration |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100% | Benny provided KB article.
1215154152466714 | Zoom to provide list of users |  |  |  | SSO and Identity Configuration
1215150263848989 | Custom SAML Mappings |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100% | Benny to provide KB article.
1215137372993424 | Site and Location Architecture |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215137372993422 | Number Inventory and Porting Readiness |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215137372993420 | Dial Plan and Telephony Architecture |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100% | Site codes bumped to 3 digits? And 3 digit exts.
1215137372993414 | Device Provisioning Strategy |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100%
1215154152466718 | Provide MAC addresses to Benny |  |  |  | Device Provisioning Strategy
1215137372993412 | E911 and Location Services |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | UCaaS | 15 days | Customer, Engineer | 100% | Based on location. MedVet will add addresses to remote Zoom users.
1215137372993715 | Determine MSI installation |  | 2026-05-08 | 2026-07-02 | Technical Discovery | Complete | Not Applicable | 15 days | Customer, Engineer | 100%
1215137372993676 | BYOC/Premise-Peering Design- Account Wide | PLANNING | 2026-05-08 | 2026-07-02 |  | In Progress | UCaaS | 15 days | Customer, Engineer | 0%
1215137372993418 | SBC / SIP interoperability (including Vocera) |  | 2026-05-08 | 2026-07-02 | BYOC/Premise-Peering Design- Account Wide | Not Started | UCaaS | 15 days | Customer, Engineer | 0%
1215150228289630 | BYOC Workshop (Discovery) |  | 2026-05-08 | 2026-07-02 | BYOC/Premise-Peering Design- Account Wide | Not Started | UCaaS | 15 days | Customer, Engineer | 0%
1215150228289629 | AudioCodes SBC Implementation (Mediant VE) |  | 2026-05-08 | 2026-07-02 | BYOC/Premise-Peering Design- Account Wide | Not Started | UCaaS | 15 days | Customer, Engineer | 0%
1215137372993671 | Integration Discovery | PLANNING | 2026-05-08 | 2026-07-02 |  | In Progress | UCaaS | 15 days | Customer, Engineer | 0%
1215137372993674 | Integration with Salesforce CRM |  | 2026-05-08 | 2026-06-10 | Integration Discovery | In Progress | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993673 | Integration with EzyVet (EHR) platform |  | 2026-05-08 | 2026-06-10 | Integration Discovery | In Progress | UCaaS | 15 days | Customer, Engineer | 0%
1215137372993680 | Authentication setup and user mapping |  | 2026-05-08 | 2026-06-10 | Integration Discovery | In Progress | UCaaS | 15 days | Customer, Engineer | 0%
1215137372993738 | API connector dependency validation |  | 2026-05-08 | 2026-06-10 | Integration Discovery | In Progress | UCaaS | 15 days | Customer, Engineer | 0%
1215137372993404 | Functional Discovery | PLANNING | 2026-05-08 | 2026-07-02 |  | In Progress | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993408 | Business goals and success criteria |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993453 | User roles and permissions |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993451 | Site and department mapping |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993449 | Auto attendants and IVR design |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993447 | Call queues and routing logic |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993445 | Business hours, after-hours, and holiday routing |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993443 | Overflow and escalation workflows |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993441 | Voicemail, greetings, and announcements |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993439 | Contact Center agent and supervisor workflows |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993437 | Reporting and dashboard requirements |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993435 | Quality Management |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | Quality Management | 15 days | Customer, Engineer | 0%
1215137372993735 | Workforce Management |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | Workforce Management | 15 days | Customer, Engineer | 0%
1215137372993433 | UAT planning and training approach |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993431 | Go-live sequencing and operational readiness |  | 2026-05-08 | 2026-06-10 | Functional Discovery | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372993849 | AI Expert Assist | PLANNING | 2026-07-03 | 2026-07-10 |  | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993850 | Discovery Workshop |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993852 | Knowledge Base |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993853 | KB: Integration Discovery (If Needed) |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993854 | KB: Upload / Sync |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993855 | Next Best Action |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993856 | Determine Use Cases |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993857 | Determine Conditions |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993858 | Determine Actions |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993859 | Determine Additional Options |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993860 | Information Retrieval |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993861 | Determine Use Cases |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993862 | Determine APIs |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993863 | Determine Intent Triggers |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993864 | Minor Feature Discussion |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993865 | Recommended Dispositions |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993866 | Smart Notes |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993867 | Automatic Translation |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993868 | Align on Go Live Plan |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215137372993869 | Approval of the Design & Plan |  | 2026-07-03 | 2026-07-10 | AI Expert Assist | Not Started | AI Expert Assist | 5 days | Customer, Engineer | 0%
1215150228289637 | Port Planning | PLANNING | 2026-07-13 | 2026-07-24 |  | Not Started | Not Applicable | 15 days | Customer, Project Manager (Primary) | 0%
1215137372993455 | Provide telco invoices and CSRs |  | 2026-07-13 | 2026-07-24 | Port Planning | Not Started | Not Applicable | 15 days | Customer, Project Manager (Primary) | 0%
1215137372993679 | Identify authorized contact on account |  | 2026-07-13 | 2026-07-24 | Port Planning | Not Started | Not Applicable | 15 days | Customer, Project Manager (Primary) | 0%
1215137372993457 | Identify numbers porting to Zoom |  | 2026-07-13 | 2026-07-24 | Port Planning | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993623 | SMS Enablement Plan | PLANNING | 2026-07-13 | 2026-07-24 |  | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993630 | 10DLC Brand application |  | 2026-07-13 | 2026-07-24 | SMS Enablement Plan | Not Started | Not Applicable | 15 days | Customer | 0%
1215137372993631 | 10DLC Campaign application UCaaS |  | 2026-07-13 | 2026-07-24 | SMS Enablement Plan | Not Started | UCaaS | 15 days | Customer | 0%
1215137372993632 | 10DLC Campaign application CCaaS |  | 2026-07-13 | 2026-07-24 | SMS Enablement Plan | Not Started | CCaaS | 15 days | Customer | 0%
1215137372993667 | Communications Plan | PLANNING | 2026-07-13 | 2026-07-24 |  | Not Started | Not Applicable | 15 days | Project Manager (Primary), Customer | 0%
1215137372993695 | Review Templates |  | 2026-07-13 | 2026-07-24 | Communications Plan | Not Started | Not Applicable | 15 days | Project Manager (Primary), Customer | 0%
1215137372993697 | Finalize Strategy |  | 2026-07-13 | 2026-07-24 | Communications Plan | Not Started | Not Applicable | 15 days | Project Manager (Primary), Customer | 0%
1215137372993669 | Training Plan | PLANNING | 2026-07-13 | 2026-07-24 |  | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993692 | Review Training Plan |  | 2026-07-13 | 2026-07-24 | Training Plan | Not Started | Not Applicable | 15 days | Customer | 0%
1215137372993693 | Coordinate Training Sessions |  | 2026-07-13 | 2026-07-24 | Training Plan | Not Started | Not Applicable | 15 days | Customer | 0%
1215137372993694 | Finalize Training Plan |  | 2026-07-13 | 2026-07-24 | Training Plan | Not Started | Not Applicable | 15 days | Customer | 0%
1215137372993681 | Onsite Resource Plan | PLANNING | 2026-07-13 | 2026-07-24 |  | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993698 | Onsite deployment services for up to 50 locations |  | 2026-07-13 | 2026-07-24 | Onsite Resource Plan | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993699 | Support for installation and activation of approximately 1,800 desk phones |  | 2026-07-13 | 2026-07-24 | Onsite Resource Plan | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993700 | Day 1: Onsite staging, device setup, and preparation for cutover |  | 2026-07-13 | 2026-07-24 | Onsite Resource Plan | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215137372993702 | Day 2: Onsite cutover support and validation |  | 2026-07-13 | 2026-07-24 | Onsite Resource Plan | Not Started | Not Applicable | 15 days | Project Manager (Primary) | 0%
1215152817791780 | Technical Implementation | ALPHA Phase | 2026-07-29 | 2026-08-19 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153102767090 | Build and Provision |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153102767102 | Users and Common Areas |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215152771159904 | Auto Receptionists, Call Queues, Recordings |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215152771159916 | Business/Holiday Hours |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215152771159928 | Desk phone (MAC addresses) |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215152771160097 | E911 and Location Services |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215137372993732 | Account Settings Configuration |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215137372993733 | User Acceptance Testing |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215137372994018 | UAT Sign Off |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Customer | 0%
1215152771160133 | AudioCodes SBC Implementation (Mediant VE) | ALPHA Phase | 2026-07-29 | 2026-08-19 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215152771160144 | SBC / SIP interoperability (including Vocera) |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215152771160156 | BYOC Trunk Group Creation |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215137372993996 | Submit Ticket To Zoom |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215137372993997 | BYOC Testing |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215137372994025 | BYOC Sign Off |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215152817792216 | Integration Implementation | ALPHA Phase | 2026-07-29 | 2026-08-19 |  | Not Started | Integrations | 15 days | Customer | 0%
1215152817792227 | Salesforce CRM |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153102768539 | EzyVet (EHR) platform |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215137372994027 | Integration Testing |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215137372994029 | Integration Sign Off |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153102768553 | Functional Implementation | ALPHA Phase | 2026-07-29 | 2026-08-19 |  | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215152950778833 | Build agents and supervisors |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372994039 | Assign roles and permissions |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215152950778889 | Build flows and queues |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372994031 | Build Inboxes |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215152950779021 | Business hours, after-hours, and holiday routing |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372994033 | Build Asset Library |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372994035 | Build Dispositions |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372994037 | Skills Created |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215152814288504 | User Acceptance Testing |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215137372994040 | UAT Sign Off |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215152817793510 | Port Submission | ALPHA Phase | 2026-07-31 | 2026-09-01 |  | Not Started | UCaaS | 21 days | Customer, Project Manager (Primary) | 0%
1215152817793526 | Prepare Port Request |  | 2026-07-31 | 2026-09-01 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215152817793538 | Prepare LOA for Signature |  | 2026-07-31 | 2026-09-01 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215152950779418 | Submit Request to Zoom |  | 2026-07-31 | 2026-09-01 | Port Submission | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153102777478 | Communications Coordination | ALPHA Phase | 2026-08-19 | 2026-08-25 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153102777489 | Send Email #1 Announcement |  |  | 2026-08-05 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153102777496 | Send Email #2 Training |  |  | 2026-08-19 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215137372993988 | Send Email #3 Go Live |  |  | 2026-09-02 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215152771086772 | Training Coordination | ALPHA Phase | 2026-08-19 | 2026-08-25 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152771170913 | Send Training Invitations |  | 2026-08-19 | 2026-08-25 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152771170920 | Deliver Training Sessions |  | 2026-08-19 | 2026-08-25 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152771170927 | Provide Training Recording and Resources |  | 2026-08-19 | 2026-08-25 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152771170934 | Onsite Resource Coordination | ALPHA Phase | 2026-08-26 | 2026-09-01 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152814304656 | Onsite deployment services for up to 50 locations |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152814304663 | Support for installation and activation of approximately 1,800 desk phones |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215152814304670 | Day 1: Onsite staging, device setup, and preparation for cutover |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215152814304677 | Day 2: Onsite cutover support and validation |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215137372993990 | Go Live | ALPHA Phase |  | 2026-09-02 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215137372994115 | Review Go Live Readiness |  |  | 2026-09-02 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215137372994128 | Zoom Phone |  |  |  | Review Go Live Readiness
1215137372994129 | Zoom Contact Center |  |  |  | Review Go Live Readiness
1215137372994130 | Quality Management |  |  |  | Review Go Live Readiness
1215137372994131 | Workforce Management |  |  |  | Review Go Live Readiness
1215137372994132 | AI Expert Assist |  |  |  | Review Go Live Readiness
1215137372994133 | Integrations |  |  |  | Review Go Live Readiness
1215137372994139 | Production integration validation |  |  |  | Integrations
1215137372994140 | EzyVet production workflow verification |  |  |  | Integrations
1215137372994141 | Salesforce production workflow verification |  |  |  | Integrations
1215137372994142 | Vocera interoperability validation |  |  |  | Integrations
1215137372994143 | Authentication and user sync validation |  |  |  | Integrations
1215137372994144 | Hypercare support for integrations |  |  |  | Integrations
1215137372994145 | Go-live issue triage and resolution |  |  |  | Integrations
1215137372994123 | Go/No Go Decision |  |  | 2026-09-02 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215137372994157 | Go Live Event |  |  | 2026-09-02 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215137372994126 | Post-Go Live Hypercare |  |  | 2026-09-02 | Go Live | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215137372994146 | Administrator Training |  |  | 2026-09-02 | Go Live | Not Started | Not Applicable | 5 days | Engineer | 0%
1216434810694053 | Technical Implementation | ALPHA+ Phase | 2026-07-29 | 2026-08-19 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1216434810694064 | Build and Provision |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434810694074 | Users and Common Areas |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716114286 | Auto Receptionists, Call Queues, Recordings |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716080153 | Business/Holiday Hours |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716080165 | Desk phone (MAC addresses) |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716115738 | E911 and Location Services |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716115750 | Account Settings Configuration |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434794588895 | User Acceptance Testing |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1216434794588907 | UAT Sign Off |  | 2026-07-29 | 2026-08-19 | Technical Implementation | Not Started | UCaaS | 15 days | Customer | 0%
1216434794588919 | AudioCodes SBC Implementation (Mediant VE) | ALPHA+ Phase | 2026-07-29 | 2026-08-19 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716117156 | SBC / SIP interoperability (including Vocera) |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1216434716117168 | BYOC Trunk Group Creation |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1216434830591462 | Submit Ticket To Zoom |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1216434830591474 | BYOC Testing |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1216434830591486 | BYOC Sign Off |  | 2026-07-29 | 2026-08-19 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1216434650395123 | Integration Implementation | ALPHA+ Phase | 2026-07-29 | 2026-08-19 |  | Not Started | Integrations | 15 days | Customer | 0%
1216434650395139 | Salesforce CRM |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1216434830601874 | EzyVet (EHR) platform |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1216434830601886 | Integration Testing |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1216434830601898 | Integration Sign Off |  | 2026-07-29 | 2026-08-19 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1216434794599022 | Functional Implementation | ALPHA+ Phase | 2026-07-29 | 2026-08-19 |  | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434794599038 | Build agents and supervisors |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810750494 | Assign roles and permissions |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810750506 | Build flows and queues |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810750518 | Build Inboxes |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810759928 | Business hours, after-hours, and holiday routing |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810759940 | Build Asset Library |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810759952 | Build Dispositions |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810768252 | Skills Created |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434810768264 | User Acceptance Testing |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434794618173 | UAT Sign Off |  | 2026-07-29 | 2026-08-19 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1216434794618185 | Port Submission | ALPHA+ Phase | 2026-07-31 | 2026-09-01 |  | Not Started | UCaaS | 21 days | Customer, Project Manager (Primary) | 0%
1216434794618201 | Prepare Port Request |  | 2026-07-31 | 2026-09-01 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1216434650423834 | Prepare LOA for Signature |  | 2026-07-31 | 2026-09-01 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1216434650423846 | Submit Request to Zoom |  | 2026-07-31 | 2026-09-01 | Port Submission | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434810778037 | Communications Coordination | ALPHA+ Phase | 2026-08-19 | 2026-08-25 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434810778053 | Send Email #1 Announcement |  | 2026-08-19 | 2026-08-25 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434810778065 | Send Email #2 Training |  | 2026-08-19 | 2026-08-25 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434650425253 | Send Email #3 Go Live |  | 2026-08-19 | 2026-08-25 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434650425265 | Training Coordination | ALPHA+ Phase | 2026-08-19 | 2026-08-25 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434830631070 | Send Training Invitations |  | 2026-08-19 | 2026-08-25 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434830631082 | Deliver Training Sessions |  | 2026-08-19 | 2026-08-25 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434810826575 | Provide Training Recording and Resources |  | 2026-08-19 | 2026-08-25 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434810826587 | Onsite Resource Coordination | ALPHA+ Phase | 2026-08-26 | 2026-09-01 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434810826603 | Onsite deployment services for up to 50 locations |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434716208355 | Support for installation and activation of approximately 1,800 desk phones |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434716208367 | Day 1: Onsite staging, device setup, and preparation for cutover |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434830676398 | Day 2: Onsite cutover support and validation |  | 2026-08-26 | 2026-09-01 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434830676410 | Go Live | ALPHA+ Phase |  | 2026-09-03 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434830676426 | Review Go Live Readiness |  |  | 2026-09-03 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434810836483 | Zoom Phone |  |  |  | Review Go Live Readiness
1216434810836490 | Zoom Contact Center |  |  |  | Review Go Live Readiness
1216434810836497 | Quality Management |  |  |  | Review Go Live Readiness
1216434716210768 | Workforce Management |  |  |  | Review Go Live Readiness
1216434716210775 | AI Expert Assist |  |  |  | Review Go Live Readiness
1216434716210782 | Integrations |  |  |  | Review Go Live Readiness
1216434716210789 | Production integration validation |  |  |  | Integrations
1216434716210796 | EzyVet production workflow verification |  |  |  | Integrations
1216434810847048 | Salesforce production workflow verification |  |  |  | Integrations
1216434810847055 | Vocera interoperability validation |  |  |  | Integrations
1216434810847062 | Authentication and user sync validation |  |  |  | Integrations
1216434810847069 | Hypercare support for integrations |  |  |  | Integrations
1216434810847076 | Go-live issue triage and resolution |  |  |  | Integrations
1216434810854443 | Go/No Go Decision |  |  | 2026-09-03 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434810854455 | Go Live Event |  |  | 2026-09-03 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1216434810854467 | Post-Go Live Hypercare |  |  | 2026-09-03 | Go Live | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1216434650470878 | Administrator Training |  |  | 2026-09-03 | Go Live | Not Started | Not Applicable | 5 days | Engineer | 0%
1215153612526657 | Technical Implementation | PILOT Phase | 2026-08-11 | 2026-08-25 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153671394030 | Build and Provision |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153671394040 | Users and Common Areas |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153651523229 | Auto Receptionists, Call Queues, Recordings |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153651523241 | Business/Holiday Hours |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153651523253 | Desk phone (MAC addresses) |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153612588148 | E911 and Location Services |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153612588160 | Account Settings Configuration |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153612588332 | User Acceptance Testing |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153612588344 | UAT Sign Off |  | 2026-08-11 | 2026-08-25 | Technical Implementation | Not Started | UCaaS | 15 days | Customer | 0%
1215153612588356 | AudioCodes SBC Implementation (Mediant VE) | PILOT Phase | 2026-08-11 | 2026-08-25 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153469508883 | SBC / SIP interoperability (including Vocera) |  | 2026-08-11 | 2026-08-25 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153469508895 | BYOC Trunk Group Creation |  | 2026-08-11 | 2026-08-25 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153651580867 | Submit Ticket To Zoom |  | 2026-08-11 | 2026-08-25 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153651580879 | BYOC Testing |  | 2026-08-11 | 2026-08-25 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153651580891 | BYOC Sign Off |  | 2026-08-11 | 2026-08-25 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153671405016 | Integration Implementation | PILOT Phase | 2026-08-11 | 2026-08-25 |  | Not Started | Integrations | 15 days | Customer | 0%
1215153671405032 | Salesforce CRM |  | 2026-08-11 | 2026-08-25 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153612588848 | EzyVet (EHR) platform |  | 2026-08-11 | 2026-08-25 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153612588860 | Integration Testing |  | 2026-08-11 | 2026-08-25 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153612588872 | Integration Sign Off |  | 2026-08-11 | 2026-08-25 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153607832031 | Functional Implementation | PILOT Phase | 2026-08-11 | 2026-08-25 |  | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153607832047 | Build agents and supervisors |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153469512593 | Assign roles and permissions |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153469512605 | Build flows and queues |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153469512617 | Build Inboxes |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153612589207 | Business hours, after-hours, and holiday routing |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153612589219 | Build Asset Library |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153612589231 | Build Dispositions |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153651581995 | Skills Created |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153651582007 | User Acceptance Testing |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153651582051 | UAT Sign Off |  | 2026-08-11 | 2026-08-25 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153651582063 | Port Submission | PILOT Phase | 2026-08-07 | 2026-09-08 |  | Not Started | UCaaS | 21 days | Customer, Project Manager (Primary) | 0%
1215153651582079 | Prepare Port Request |  | 2026-08-07 | 2026-09-08 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215153612590578 | Prepare LOA for Signature |  | 2026-08-07 | 2026-09-08 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215153612590590 | Submit Request to Zoom |  | 2026-08-07 | 2026-09-08 | Port Submission | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153612598928 | Communications Coordination | PILOT Phase | 2026-07-27 | 2026-08-24 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153612598944 | Send Email #1 Announcement |  |  | 2026-08-11 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153612598956 | Send Email #2 Training |  |  | 2026-08-25 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153607848120 | Send Email #3 Go Live |  |  | 2026-09-08 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153607848132 | Training Coordination | PILOT Phase | 2026-08-25 | 2026-08-31 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153469517479 | Send Training Invitations |  | 2026-08-25 | 2026-08-31 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153469517491 | Deliver Training Sessions |  | 2026-08-25 | 2026-08-31 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153469517503 | Provide Training Recording and Resources |  | 2026-08-25 | 2026-08-31 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153651589651 | Onsite Resource Coordination | PILOT Phase | 2026-09-01 | 2026-09-07 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153607873359 | Onsite deployment services for up to 50 locations |  | 2026-09-01 | 2026-09-07 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153607873371 | Support for installation and activation of approximately 1,800 desk phones |  | 2026-09-01 | 2026-09-07 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153607873383 | Day 1: Onsite staging, device setup, and preparation for cutover |  | 2026-09-01 | 2026-09-07 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153671454424 | Day 2: Onsite cutover support and validation |  | 2026-09-01 | 2026-09-07 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153671454436 | Go Live | PILOT Phase |  | 2026-09-08 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153671454516 | Review Go Live Readiness |  |  | 2026-09-08 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153671454528 | Zoom Phone |  |  |  | Review Go Live Readiness
1215153671454535 | Zoom Contact Center |  |  |  | Review Go Live Readiness
1215153671454542 | Quality Management |  |  |  | Review Go Live Readiness
1215153469526932 | Workforce Management |  |  |  | Review Go Live Readiness
1215153469526939 | AI Expert Assist |  |  |  | Review Go Live Readiness
1215153469526946 | Integrations |  |  |  | Review Go Live Readiness
1215153469526953 | Production integration validation |  |  |  | Integrations
1215153671455983 | EzyVet production workflow verification |  |  |  | Integrations
1215153671455990 | Salesforce production workflow verification |  |  |  | Integrations
1215153671455997 | Vocera interoperability validation |  |  |  | Integrations
1215153671456004 | Authentication and user sync validation |  |  |  | Integrations
1215153671456011 | Hypercare support for integrations |  |  |  | Integrations
1215153671464255 | Go-live issue triage and resolution |  |  |  | Integrations
1215153671464262 | Go/No Go Decision |  |  | 2026-09-08 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215137372994161 | Go Live Event |  |  | 2026-09-08 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153671464274 | Post-Go Live Hypercare |  |  | 2026-09-08 | Go Live | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153607883157 | Administrator Training |  |  | 2026-09-08 | Go Live | Not Started | Not Applicable | 5 days | Engineer | 0%
1215153937286721 | Technical Implementation | WAVE 1 Phase | 2026-08-17 | 2026-09-14 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153653894152 | Build and Provision |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153653894162 | Users and Common Areas |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153653894172 | Auto Receptionists, Call Queues, Recordings |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153610102719 | Business/Holiday Hours |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153614842886 | Desk phone (MAC addresses) |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153614842898 | E911 and Location Services |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153614842910 | Account Settings Configuration |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153745493533 | User Acceptance Testing |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153745493545 | UAT Sign Off |  | 2026-08-17 | 2026-09-14 | Technical Implementation | Not Started | UCaaS | 15 days | Customer | 0%
1215153610103459 | AudioCodes SBC Implementation (Mediant VE) | WAVE 1 Phase | 2026-08-17 | 2026-09-14 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153610103475 | SBC / SIP interoperability (including Vocera) |  | 2026-08-17 | 2026-09-14 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153610103487 | BYOC Trunk Group Creation |  | 2026-08-17 | 2026-09-14 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153937518541 | Submit Ticket To Zoom |  | 2026-08-17 | 2026-09-14 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153937518553 | BYOC Testing |  | 2026-08-17 | 2026-09-14 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153937518662 | BYOC Sign Off |  | 2026-08-17 | 2026-09-14 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153937518674 | Integration Implementation | WAVE 1 Phase | 2026-08-17 | 2026-09-14 |  | Not Started | Integrations | 15 days | Customer | 0%
1215153937518690 | Salesforce CRM |  | 2026-08-17 | 2026-09-14 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153745502371 | EzyVet (EHR) platform |  | 2026-08-17 | 2026-09-14 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153745502383 | Integration Testing |  | 2026-08-17 | 2026-09-14 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153653904104 | Integration Sign Off |  | 2026-08-17 | 2026-09-14 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153653904116 | Functional Implementation | WAVE 1 Phase | 2026-08-17 | 2026-09-14 |  | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153653904132 | Build agents and supervisors |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153937526224 | Assign roles and permissions |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153937526236 | Build flows and queues |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153937526408 | Build Inboxes |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153937526420 | Business hours, after-hours, and holiday routing |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153937526432 | Build Asset Library |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153614885691 | Build Dispositions |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153614885703 | Skills Created |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153614885715 | User Acceptance Testing |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153745513241 | UAT Sign Off |  | 2026-08-17 | 2026-09-14 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153745513253 | Port Submission | WAVE 1 Phase | 2026-08-12 | 2026-09-15 |  | Not Started | UCaaS | 21 days | Customer, Project Manager (Primary) | 0%
1215153745513493 | Prepare Port Request |  | 2026-08-12 | 2026-09-15 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215153745513505 | Prepare LOA for Signature |  | 2026-08-12 | 2026-09-15 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215153745513517 | Submit Request to Zoom |  | 2026-08-12 | 2026-09-15 | Port Submission | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153745513658 | Communications Coordination | WAVE 1 Phase | 2026-08-18 | 2026-09-15 |  | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153745513674 | Send Email #1 Announcement |  |  | 2026-08-18 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153610107734 | Send Email #2 Training |  |  | 2026-09-01 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153610107746 | Send Email #3 Go Live |  |  | 2026-09-15 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153610107758 | Training Coordination | WAVE 1 Phase | 2026-09-01 | 2026-09-07 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153653924569 | Send Training Invitations |  | 2026-09-01 | 2026-09-07 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153653924581 | Deliver Training Sessions |  | 2026-09-01 | 2026-09-07 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153937535442 | Provide Training Recording and Resources |  | 2026-09-01 | 2026-09-07 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153614817389 | Onsite Resource Coordination | WAVE 1 Phase | 2026-09-08 | 2026-09-14 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153745564569 | Onsite deployment services for up to 50 locations |  | 2026-09-08 | 2026-09-14 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153745564581 | Support for installation and activation of approximately 1,800 desk phones |  | 2026-09-08 | 2026-09-14 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153653953948 | Day 1: Onsite staging, device setup, and preparation for cutover |  | 2026-09-08 | 2026-09-14 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153653953960 | Day 2: Onsite cutover support and validation |  | 2026-09-08 | 2026-09-14 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153653953972 | Go Live | WAVE 1 Phase |  | 2026-09-15 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153614900934 | Review Go Live Readiness |  |  | 2026-09-15 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153614900946 | Zoom Phone |  |  |  | Review Go Live Readiness
1215153614900953 | Zoom Contact Center |  |  |  | Review Go Live Readiness
1215153614901376 | Quality Management |  |  |  | Review Go Live Readiness
1215153614901383 | Workforce Management |  |  |  | Review Go Live Readiness
1215153614901390 | AI Expert Assist |  |  |  | Review Go Live Readiness
1215153614901397 | Integrations |  |  |  | Review Go Live Readiness
1215153937564444 | Production integration validation |  |  |  | Integrations
1215153937564451 | EzyVet production workflow verification |  |  |  | Integrations
1215153937564458 | Salesforce production workflow verification |  |  |  | Integrations
1215153937564465 | Vocera interoperability validation |  |  |  | Integrations
1215153937564472 | Authentication and user sync validation |  |  |  | Integrations
1215153653958181 | Hypercare support for integrations |  |  |  | Integrations
1215153653958188 | Go-live issue triage and resolution |  |  |  | Integrations
1215153653958195 | Go/No Go Decision |  |  | 2026-09-15 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153653958207 | Go Live Event |  |  | 2026-09-15 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153937566897 | Post-Go Live Hypercare |  |  | 2026-09-15 | Go Live | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153937566909 | Administrator Training |  |  | 2026-09-15 | Go Live | Not Started | Not Applicable | 5 days | Engineer | 0%
1215153892401384 | Technical Implementation | WAVE 2 Phase | 2026-08-10 | 2026-09-22 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153892401395 | Build and Provision |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940013960 | Users and Common Areas |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940013970 | Auto Receptionists, Call Queues, Recordings |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940013980 | Business/Holiday Hours |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153747964265 | Desk phone (MAC addresses) |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153747964277 | E911 and Location Services |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153747964289 | Account Settings Configuration |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153748021388 | User Acceptance Testing |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Engineer | 0%
1215153748021400 | UAT Sign Off |  | 2026-08-10 | 2026-09-22 | Technical Implementation | Not Started | UCaaS | 15 days | Customer | 0%
1215153940016777 | AudioCodes SBC Implementation (Mediant VE) | WAVE 2 Phase | 2026-08-10 | 2026-09-22 |  | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940016793 | SBC / SIP interoperability (including Vocera) |  | 2026-08-10 | 2026-09-22 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940016805 | BYOC Trunk Group Creation |  | 2026-08-10 | 2026-09-22 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153748036113 | Submit Ticket To Zoom |  | 2026-08-10 | 2026-09-22 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153748036125 | BYOC Testing |  | 2026-08-10 | 2026-09-22 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940020322 | BYOC Sign Off |  | 2026-08-10 | 2026-09-22 | AudioCodes SBC Implementation (Mediant VE) | Not Started | UCaaS | 15 days | Engineer | 0%
1215153940020334 | Integration Implementation | WAVE 2 Phase | 2026-08-10 | 2026-09-22 |  | Not Started | Integrations | 15 days | Customer | 0%
1215153940020350 | Salesforce CRM |  | 2026-08-10 | 2026-09-22 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153915590495 | EzyVet (EHR) platform |  | 2026-08-10 | 2026-09-22 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153915590507 | Integration Testing |  | 2026-08-10 | 2026-09-22 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153748045763 | Integration Sign Off |  | 2026-08-10 | 2026-09-22 | Integration Implementation | Not Started | Integrations | 15 days | Customer | 0%
1215153748045775 | Functional Implementation | WAVE 2 Phase | 2026-08-10 | 2026-09-22 |  | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153748045791 | Build agents and supervisors |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153915599083 | Assign roles and permissions |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153915599095 | Build flows and queues |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153748055723 | Build Inboxes |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153748055735 | Business hours, after-hours, and holiday routing |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153748055747 | Build Asset Library |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153915610495 | Build Dispositions |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153915610507 | Skills Created |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153915610519 | User Acceptance Testing |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153748065526 | UAT Sign Off |  | 2026-08-10 | 2026-09-22 | Functional Implementation | Not Started | CCaaS | 15 days | Customer, Engineer | 0%
1215153748065538 | Port Submission | WAVE 2 Phase | 2026-08-10 | 2026-09-22 |  | Not Started | UCaaS | 21 days | Customer, Project Manager (Primary) | 0%
1215153912240862 | Prepare Port Request |  | 2026-08-10 | 2026-09-22 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215153912240874 | Prepare LOA for Signature |  | 2026-08-10 | 2026-09-22 | Port Submission | Not Started | Not Applicable | 1 day | Customer | 0%
1215153912240886 | Submit Request to Zoom |  | 2026-08-10 | 2026-09-22 | Port Submission | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153748003972 | Communications Coordination | WAVE 2 Phase | 2026-08-10 | 2026-09-22 |  | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153748003988 | Send Email #1 Announcement |  |  | 2026-08-25 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153915626379 | Send Email #2 Training |  |  | 2026-09-08 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153915626391 | Send Email #3 Go Live |  |  | 2026-09-22 | Communications Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153748112347 | Training Coordination | WAVE 2 Phase | 2026-08-26 | 2026-09-07 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153748112363 | Send Training Invitations |  | 2026-08-26 | 2026-09-07 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153748112375 | Deliver Training Sessions |  | 2026-08-26 | 2026-09-07 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153940093453 | Provide Training Recording and Resources |  | 2026-08-26 | 2026-09-07 | Training Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153940093465 | Onsite Resource Coordination | WAVE 2 Phase | 2026-09-07 | 2026-09-21 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153915651795 | Onsite deployment services for up to 50 locations |  | 2026-09-07 | 2026-09-21 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153915651807 | Support for installation and activation of approximately 1,800 desk phones |  | 2026-09-07 | 2026-09-21 | Onsite Resource Coordination | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153915651819 | Day 1: Onsite staging, device setup, and preparation for cutover |  | 2026-09-07 | 2026-09-21 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153912266256 | Day 2: Onsite cutover support and validation |  | 2026-09-07 | 2026-09-21 | Onsite Resource Coordination | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153912266268 | Go Live | WAVE 2 Phase |  | 2026-09-22 |  | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153915652047 | Review Go Live Readiness |  |  | 2026-09-22 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153915652059 | Zoom Phone |  |  |  | Review Go Live Readiness
1215153915652066 | Zoom Contact Center |  |  |  | Review Go Live Readiness
1215153915652073 | Quality Management |  |  |  | Review Go Live Readiness
1215153912268738 | Workforce Management |  |  |  | Review Go Live Readiness
1215153912268745 | AI Expert Assist |  |  |  | Review Go Live Readiness
1215153912268752 | Integrations |  |  |  | Review Go Live Readiness
1215153912268759 | Production integration validation |  |  |  | Integrations
1215153912268932 | EzyVet production workflow verification |  |  |  | Integrations
1215153912268939 | Salesforce production workflow verification |  |  |  | Integrations
1215153912268946 | Vocera interoperability validation |  |  |  | Integrations
1215153912268953 | Authentication and user sync validation |  |  |  | Integrations
1215153912268960 | Hypercare support for integrations |  |  |  | Integrations
1215153892576175 | Go-live issue triage and resolution |  |  |  | Integrations
1215153892576182 | Go/No Go Decision |  |  | 2026-09-22 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153892576194 | Go Live Event |  |  | 2026-09-22 | Go Live | Not Started | Not Applicable | 1 day | Project Manager (Primary) | 0%
1215153748132649 | Post-Go Live Hypercare |  |  | 2026-09-22 | Go Live | Not Started | Not Applicable | 5 days | Project Manager (Primary) | 0%
1215153748132661 | Administrator Training |  |  | 2026-09-22 | Go Live | Not Started | Not Applicable | 5 days | Engineer | 0%